## Sheet1
Sl.No | Activities | Hours | Remarks
1 | Undestand the existing implementation |  | Analysing the existing code
| Undestand the Java Implemenation | 8
| Understand the script and cron scheduling | 4
| Check the SOAP Service through SOAP UI | 4
2 | Implemenation
| Get the record from Salesforce | 8 | May be we can reuse the existing code
| Calling the SOAP Service - 1 | 8
| Calling the SOAP Service - 2 | 8
| Validation and error handling | 8
| Processing success records | 6
| Processing error records | 4
| Sending update status through mail | 4
| DB changes | 4
3 | Testing and UAT Deployment
| Local Testing and UAT Testing | 8
| Deployment | 3
4 | Documentation
| Confluence Update | 6
5 | Total
6
7