## Sheet1
Sl.No | Activities | Owner | Hours | Remarks
1 | Development Environment setup |  | 2020-03-04 | Workspace Setup for Developers
| Dev environment set up for spring boot | Sam
| Dev environment set up for Angular | XXX
| Dev environment set up for DB | Thangam
2 | Requirement study |  | 2020-03-04 | Through whiteboarding and discussions
| Understanding the requirement | All
| Understanding the data sheet | All
| Understanding the front end | XXX
| Understanding the rules & SI calculation | Sam
| Understanding the display requirement | Sam/XXX
3 | Database setup |  | 2020-03-04 | Setting up in Magic Lab
| Create database tables | Thangam
| Backend data upload to DB | Thangam
| Preparation of Queries to front end and back end | Thangam
4 | Development
| Front end | XXX | 2020-03-06 | All screens to be completed
| Backend | Sam | 2020-03-06 | Rules logic, calculation of SI, sending data to Front end
5 | Integration
| Backend with Front end | XXX,Sam | 2020-03-17 | Independent components to be integrated
| DB with Backend and Front end | XXX,Sam, Thangam | 2020-03-17 | All integration if there had been any stub
6 | Testing
| With the data and multiple scenario |  | 2020-03-18 | Sample data to be used to do parallel run
7 | Deliver for Demo |  | 2020-03-20